## Project Charter
This Project Charter is provided to you by ExcelMadeEasy. By ExcelMadeEasy | ExcelMadeEasy.com
A project charter is part of the initial project planning package. It gives the Project Manager the authority and means to do his project.
Project name | Project XYZ
Company Name | The company
Company Address
Date | Wednesday April 2, 2015
Authorization | This Charter formally authorizes the Project XYZ. A project plan will be developed and submitted to the Project Sponsor for approval. The project plan will include: scope statement, requirements, organisation, timing, cost estimate, budget, resource, quality expectation, expected risks as project control. All resources will be approved by the Sponsor.
Project Scope | Specifiy deliverables, business needs, problems or opportunities, market demand, legal requirement, customer need, technological advancement
Project Management and authority | The Project Manager, xyz, is hereby authorized to interface with management as required, negotiate for resources, delegate responsibilities within the framework of the project, and to communicate with all contractors and management, as required, to ensure successful and timely completion of the project. The Project Manager is responsible for developing the project plan, monitoring the schedule, cost, and scope of the project during implementation, and maintaining control over the project by measuring performance and taking corrective action.
Project Budget and sources of funding | total budget of $xxxxxx. Budget comes from the R&D Budget of Mr.ABC
Main Milestones | 1.1.2015: project scope planned and approved
11.1.2015: project kick off
31.5.2015: development phase complete
31.7.2015: samples delivered and approved
31.8.2015: training started
15.11.2015: production preparation completed
1.12.2015: production start
add any other important mile stone
Approvals
Sponsors signature
Project Manager signatures
Attachement: | organisation, budget, RASIC, timing plan.